## Thesis Planner
Project Planner
*Re-submission is to be done only if any changes to the final project are requested from the examiner. | [8 empty] | Period Highlight: | 12 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) |  |  |  | Planned holidays
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | DISRUPTION START | DISRUPTION DURATION | DISRUPTION 2 START | DISRUPTION 2 DURATION | PERCENT COMPLETE | December | [19 empty] | January
[10 empty] | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Project Proposal | 12 | 2 | 12 | 2 | 0 | 0 | 0 | 0 | 100%
Project Approval | 14 | 3 | 14 | 0 | 0 | 0 | 0 | 0 | 0%
GUI | 17 | 7 | [6 empty] | 0%
Classes part 1 | 17 | 15 |  |  | 24 | 2 | 30 | 2 | 0%
Classes part 2 | 1 | 4 |  |  | 1 | 1 |  |  | 0%
Testing | 2 | 5 | [6 empty] | 0%
Submission | 7 | 1 | [6 empty] | 0%
Re-submission* | 9 | 3 | [6 empty] | 0%